## General
Team Number: | 3
Week: | 2

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Start marking up front end UI
2 | Have shellinthebox run in minion nodes
3 | Draft salt modules for getting container information between machines
4
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Get members set up with Vagrant
2 | Get memebers setup with Git
3 | Establish how we're going to communicate
4 | Establish whether or not we're going to use keystone.js or vanilla MEAN stack; we're using keystone.js
5 | Get comfortable with frontend framework
6 | Get Vagrant files and salt config files setup for LXC
7
8

## Risk
Top Project Risks as of 02/19/2015
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Members may have unexpected situations at work / unexpected obligations | Document / note any work so that others can pick up slack
3 | 2 | Members aren't able to attend a meeting | Take minutes
2 | - | Some team members machines might not be powerful enough to run multiple VMs | Dual boot lightwieght linux distro / document occurances where RAM becomes an issue

## COTS
List of third-party components being considered for use in the system as of 02/12/2015
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Vagrant | Virtual Machine Managment | Linux, Ruby | Maintaing development/production machines
Salt | Automatic Machine Configuration | Linux, Python | Machine communication and automatic configuration
Shellinabox | Terminal emualtor in the browser | Linux | User terminal session
Keystone.js | Node.js CMS + MVC | MongoDB, ExpressJS, NodeJS | User authentication and document management
AdminLTE | CSS Framework | Bootstrap | UI Elements, eye candy

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Salt hangs if config file starts shellinabox or installs a .deb that starts a service | Use Vagrant to deploy shellinabox
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | KeystoneJS's login system and admin UI framework are inflexible | Look into modifying some of the core components of Keystone
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Not all members are experienced as others with the technology we are using | Training and status checks posted in a central place
2
3
4
5