## General
Team Number: | 3
Week: | 7

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Restructured the Front End (for easer testing)
2 | Finish Websockets for Shellinabox
3 | Write installer
4 | Review and break down sprint 3
5 | Refactor LXC control daemon
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Implement the ability to turn off and on lxc containers via salt.
2 | implement the ability to get lxc usage
3 | Get ready for Sprint 2 demo
4
5
6
7
8

## Risk
Top Project Risks as of 03/26/2015
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Members may have unexpected situations at work / unexpected obligations | Document / note any work so that others can pick up slack
1 | 1 | Members get sick and are unable to work on the project | Document / note any work so that others can pick up slack
2 | 2 | Members aren't able to attend a meeting | Take minutes
3 | 3 | Some team members machines might not be powerful enough to run multiple VMs | Dual boot lightwieght linux distro / document occurances where RAM becomes an issue
4 | 4 | DigitalOcean Repository Mirrors are slow sometimes | In provisoning scripts, add better mirrors (to be done)
2 | 2 | Decision to refactor using new framework can backfire | Using scaffolding from previous projects, write modules in such a way so that they can be put somewhere else if needed

## COTS
List of third-party components being considered for use in the system as of 03/26/2015
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Vagrant | Virtual Machine Managment | Linux, Ruby | Maintaing development/production machines
Salt | Automatic Machine Configuration | Linux, Python | Machine communication and automatic configuration
Shellinabox | Terminal emualtor in the browser | Linux | User terminal session
Keystone.js | Node.js CMS + MVC | MongoDB, ExpressJS, NodeJS | User authentication and document management
AdminLTE | CSS Framework | Bootstrap | UI Elements, eye candy
Feather.JS | Node JS REST API Framework | MongoDB, ExpressJS, NodeJS | API Endpoints
Passport | Authentication | NodeJS | User Authentication
PHPUnit | REST Enpoint Testing | NodeJS | Testing
PhantomJS | Headless Web Client | - | Visual Diffs
APIBluePrint | API Description Language | - | Reference material / documentation

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Members became ill | Document work so we can delegate effectively. Practice good hygiene
2 | Midterms / Exams | Tell the team well in advance about midterms
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Not all members are experienced as others with the technology we are using | Training and status checks posted in a central place
2
3
4
5